## SUIVI DOCUMENTAIRE
DOCUMENT LIST & SCHEDULE FOR BELT FILTER
| Customer's Name | Boliden Rönnskär | [8 empty] | Approuved
| Project Name | 1xHVBF 6B10 for NiSO4 production | [8 empty] | included in / NA
| HASLER Document Number | SD0130-DL_01
| Customer Document ID | 1018739-HAS-0035
| Contrat date | 2025-05-21
| PO Number | 1018739/RON
Item | HASLER Document Number | Customer Document ID | Customer Document Code | Document Description | Customer approval | Expected Submittal Date | Revision | Submittal Date | Cutomer expected return date | Customer return status | Document Status | Remarks
1 |  |  |  | PROJECT MANAGEMENT
1.1 | SD0130-SCH_01 | 1018739-HAS-0002 |  | Project schedule (Design, fabrication, installation) | Yes | 2025-06-21 | revA | 2025-06-24 | 2025-07-01
[7 empty] | revD | 2025-10-30 | 2025-11-06
[7 empty] | revH | 2026-01-29 | 2026-02-05 | Approved
1.2 | SD0130-COMP_01 | 1018739-HAS-0003 |  | Commissioning program | Yes | 2026-04-01 | revA | 2026-02-06 | 2026-02-13 | Approved |  | for detail please see file already sent : "Hasler_Commissioning check-list-Client version-VBF-EN"
revB
revC
1.3 |  |  |  | Training program |  | NA | revA
1.2 | SD0130-COMR_01 | 1018739-HAS-0004 |  | Commissioning report | Yes | 2026-06-30 | revA |  |  |  |  | a unique report will be done at the end of comminioning.
revB
revC
1.3 | SD0130-PRO_01 | 1018739-HAS-0005 |  | Progress report | Yes | Monthly | revB | 2025-07-29 | 2025-08-05 | Commented, to be updated
[7 empty] | revC | 2025-10-01 | 2025-10-08
[7 empty] | revD | 2025-10-30 | 2025-11-06
2 |  |  |  | QUALITY
2.1 | SD0130-QAM_01 | 1018739-HAS-0006 |  | Quality assurance manual | Yes | 2025-06-10 | revA | 2025-07-28 | 2025-08-04 | Commented, to be updated
[7 empty] | revB | 2025-10-10 | 2025-10-17 | Approved
revC
2.2 | SD0130-ITP_01 | 1018739-HAS-0007 |  | Inspection, test and control plan | Yes | 2025-06-23 | revA | 2025-08-19 | 2025-08-26 | Commented, to be updated
[7 empty] | revB | 2025-10-08 | 2025-10-15 | Commented, to be updated
[7 empty] | revC | 2026-02-17 | 2026-02-24
2.3 | SD0130-EQL_01 | 1018739-HAS-0008 |  | Inspection and test reports/certificates | Yes | 2026-04-15 | revA
revB
revC
3 |  |  |  | DESIGN (General)
3.1 | SD0130-GA_01 | 1018739-HAS-3000 |  | General Assembly (filter + accessories, including main dimensions, weight, load diagram and foundation and anchor bolt specification) | Yes | 2025-07-24 | revA | 2025-07-08 | 2025-07-15 | Commented, to be updated
[7 empty] | revB | 2025-10-22 | 2025-10-29 | Commented, to be updated
[7 empty] | revC | 2025-11-21 | 2025-11-28 | Approved
3.2 | SD0130-3D_01 | 1018739-HAS-0040 |  | Document for project engineering (simplified 3D-models) | Yes | 2025-07-24 | revA | 2025-07-25 | 2025-08-01 | Approved |  | 3D-format (Native or STEP)
[7 empty] | revC | 2025-12-12 | 2025-12-19 | Approved with comments
[7 empty] | revD | 2026-02-25 | 2026-03-04 | Approved
3.3 | SD0130-CI_01 |  |  | Catalogue information (standard equipment) | Yes | Prel. in offer | revA | 2025-05-14 |  | Approved |  | Prel. in offer
revB
revC
3.4 | SD0130-TD_01 |  |  | Technical description including performance data | Yes | Prel. in offer | revA | 2025-05-14 |  | Approved |  | Prel. in offer
revB
revC
3.5 | SD0130-DS_01 | 1018739-HAS-0009 |  | Data sheets | Yes | 2025-07-23 | revA |  |  | Approved |  | See manuals Which manuals ?
[7 empty] | revB |  |  |  |  | Requested information provided by email;
revC
3.6 | SD0130-STS_01 | 1018739-HAS-0010 |  | Surface treatment specification | Yes | Prel. in offer | revA | 2026-03-17 |  |  |  | Prel. in offer
[6 empty] | 2025-06-23 | revB |  |  |  |  | One document with all paint subsupplier specification
[7 empty] | revC |  |  |  |  | All paint specification and chemical composition to be sent in ZIP files
3.7 | SD0130-ICS_01 | 1018739-HAS-0011 |  | Interface/connection specification |  | NA
3.8 | SD0130-INS-00002 | 1018739-HAS-0036 |  | Piping & instrument (P&I) Diagram | Yes | 2025-07-23 | revD | 2025-12-23 | 2025-12-30 | Commented, to be updated
[7 empty] | revE | 2026-02-09 | 2026-02-16 | Commented, to be updated
[7 empty] | revF | 2026-03-30 | 2026-04-06 | Approved
3.9 | SD0130-INS-00001 | 1018739-HAS-0037 |  | Process flow diagram | Yes |  | revC | 2025-11-21 | 2025-11-28 | Commented, to be updated
[6 empty] | 2025-07-23 | revD | 2026-02-09 | 2026-02-16 | Commented, to be updated
[7 empty] | revE | 2026-03-30 | 2026-04-06 | Approved
3.10 | SD0130-CAL_01 | 1018739-HAS-0012 |  | Calculations | Yes |  | revA | 2025-11-21 | 2025-11-28 | Approved |  | Please specify the type of calculations required
[7 empty] | revB |  |  |  |  | Boliden's feedback: I have talked to our process team, and they would like to receive a filter sizing calculation, For example; slurry feed, filtration area, belt speed, filtration rate etc,
[7 empty] | revC |  |  |  |  | Several exchanges with Zenne, all information provided
3.11 | SD0130-BOM_01 | 1018739-HAS-0013 |  | Bill of material | Yes | NA | revA
3.12 |  |  |  | Motorlist |  | Included in item 4.10 | revA |  |  |  |  | All electrical consumers in Excel format.
3.13 |  |  |  | Workshop drawings |  | NA | revA |  |  |  |  | Deflected Hasler only provide GA
3.14 | SD0130-ABD_01 | 1018739-HAS-3002 |  | As built drawings | Yes | 4 w after manufacturing | revA |  |  |  |  | Updating will be done only on the GA in case of modifications of configuration of work
revB
revC
3.15 | SD0130-TIN_01 | 1018739-HAS-0014 |  | Transport information (profile, weights, packages) | Yes | 2026-03-01 | revA |  |  |  |  | 8w before delivery
revB
revC
3.16 | SD0130-ERFQ_01 | 1018739-HAS-0015 |  | Erection requirements (tools, cranes, openings) | Yes | 2025-07-23 | revA | 2025-07-02 | 2025-07-09 | Commented, to be updated |  | ok after providing pictures/3D model of the plant
[7 empty] | revB | 2025-10-02 | 2025-10-09 | Approved
revC
3.17 | SD0130-DOI_01 | 1018739-HAS-0016 |  | Declaration of Conformity/incorporation | No | 2026-04-01 | revA |  |  |  |  | Preview 4w before delivery, final 2w before taking over
[7 empty] | revB |  |  |  |  | Okay for the delaration of conformity. But, as the automation and electrical cabinet parts are excluded from this project, it qualifies as a partly completed machinery according to the Machinery Directive 2006/42/EC. So, Hasler will provide a declaration of incorporation of partly completed machinery. A partly completed machinery according to the Machinery Directive 2006/42/EC does not have the CE marking. Only machinery have the CE marking. ok for the delay.
revC
3.18 | SD0130-RI_01 | 1018739-HAS-0017 |  | Risk analysis | No | 2025-08-13 | revA | 2025-07-24 | 2025-07-31 | Approved |  | In English and in Swedish
revB
revC
3.19 | SD0130-GA_02 | 1018739-HAS-3003 |  | General Assembly Wash Water receiver | Yes |  | revA | 2025-10-22 | 2025-10-29 | Commented, to be updated
[7 empty] | revB | 2025-10-31 | 2025-11-07 | Commented, to be updated
[7 empty] | revC | 2025-11-21 | 2025-11-28 | Approved
3.20 | SD0130-GA_03 | 1018739-HAS-3004 |  | General Assembly Filtrate receiver | Yes |  | revA | 2025-10-29 | 2025-11-05 | Commented, to be updated
[7 empty] | revB | 2025-11-21 | 2025-11-28 | Approved
revC
3.21 | SD0130-GA_04 | 1018739-HAS-3005 |  | General Assembly Drip pan | Yes |  | revA | 2025-10-17 | 2025-10-24 | Commented, to be updated
[7 empty] | revB | 2025-11-05 | 2025-11-12 | Approved
revC
4 |  |  |  | ELECTRICAL DESIGN
4.1 | SD0130-CCS_01 | 1018739-HAS-0038 |  | Control cabinet sizes | No | Included in 4.11 | revA
4.2 | SD0130-ELE-00001 | 1018739-HAS-0039 |  | Circuit diagram, cable list (electrical schema) | Yes | 8 w after PID approval | revA | 2026-02-09 | 2026-02-16 | Approved
[7 empty] | revB | 2026-03-30 | 2026-04-06
revC
4.3 | SD0130-AUT-00002 | 1018739-HAS-0018 |  | Logic diagrams | Yes | 8 w after PID approval | revA | 2026-02-09 | 2026-02-16
[7 empty] | revB | 2026-03-30 | 2026-04-06
revC
4.4 | SD0130-AUT-00001 | 1018739-HAS-0019 |  | Functional description | Yes | 8 w after PID approval | revA | 2026-02-09 | 2026-02-16
[7 empty] | revB | 2026-03-30 | 2026-04-06
revC
4.5 | SD0130-CC_01 | 1018739-HAS-0020 |  | Calibration certificate | Yes | 2026-04-01 | revA |  |  |  |  | For components (instruments, motors, etc.)
revB
revC
4.6 |  |  |  | Earthing system |  | Included in item 4.2 | revA |  |  |  |  | ok, included in electrical scheme
4.7 |  |  |  | Calculation data |  | NA | revA |  |  |  |  | Deflected Hasler can't provide this type of data.
4.8 | SD0130-INS-00003 | 1018739-HAS-0021 |  | Instrument list | Yes | 4 w after electrical drawing approval | revB | 2025-12-23 | 2025-12-30 | Commented, to be updated |  | Instrument list with all technical data in Excel format
[7 empty] | revC | 2026-02-09 | 2026-02-16 | Approved
[7 empty] | revD | 2026-03-30 | 2026-04-06 | Approved
4.9 | SD0130-INS-00004 | 1018739-HAS-0022 |  | Instrument Datasheet List | Yes | 4 w after electrical drawing approval | revB | 2025-12-23 | 2025-12-30 | Approved
[7 empty] | revC | 2026-02-09 | 2026-02-16 | Approved
[7 empty] | revD | 2026-03-30 | 2026-04-06 | Approved
4.10 | SD0130-ECL-00001 | 1018739-HAS-0023 |  | Electrical consumers list | No | 8 w after PID approval | revA | 2025-12-23 | 2025-12-30
[7 empty] | revB | 2026-02-09 | 2026-02-16
revC
4.11 | SD0130-054-00001 | 1018739-HAS-0024 |  | Local Control Panel equipment | No | 4 w after electrical drawing approval | revA | 2026-02-09 | 2026-02-16
revB
revC
4.12 | SD0130-006-00001 | 1018739-HAS-0025 |  | Junction box equipment | No | 4 w after electrical drawing approval | revA | 2026-02-09 | 2026-02-16
[7 empty] | revB | 2026-02-20 | 2026-02-27
revC
4.12 | SD0130-INSDS_01 | 1018739-HAS-0026 |  | Data sheets / manuals instrumentation | Yes | 8 w after PID and instrumentation list approval | revA
revB
revC
4.13 |  |  |  | Suggestion of cable routing |  | NA | revA
4.14 |  |  |  | Layout / PI&D with elec. / instr. Placement |  | Included in item 3.8 | revA
5 |  |  |  | FABRICATION, INSPECTION AND TESTING
5.1 | SD0130-TPRO_01 | 1018739-HAS-0027 |  | Test protocol, inspection and testing of control cabinets/boxes | No | 2026-04-01 | revA
revB
revC
5.2 | SD0130-SUB_01 | 1018739-HAS-0028 |  | Subcontractor list | No | Prel. in offer | revA | 2025-05-14 |  |  |  | Prel. in offer
[6 empty] | 2025-07-23 | revB | 2025-07-24 | 2025-07-31 | Approved |  | Hasler will give top 5 of supppliers
revC
5.3 |  |  |  | Certified drawings |  | NA | [5 empty] | #VALUE!
5.4 | SD0130-WPP_01 | 1018739-HAS-0029 |  | Welding process and procedures | No | Included in item 5.7 | revA
5.5 | SD0130-WQC_01 | 1018739-HAS-0030 |  | Welder qualification certificates | No | Included in item 5.7 | revA
5.6 | SD0130-MATC_01 | 1018739-HAS-0031 |  | Material certificates | No | Included in item 5.7 | revA
5.7 | SD0130-MDB_01 | 1018739-HAS-0041 |  | Manufacturer data book | No |  | revA | 2026-03-17 | 2026-03-24
revB
revC
6 |  |  |  | MANUALS/INSTRUCTIONS
6.1 |  |  |  | Installation instructions |  | Included in item 6.2 | revA
6.2 | SD0130-IOM_01 | 1018739-HAS-0032 |  | Operating instructions/Instructions manual | No | 2026-04-01 | revA |  |  |  |  | Example of belt filter instructions manual sent in offer.
[7 empty] | revB |  |  |  |  | Will be translated in Swedish
[7 empty] | revC |  |  |  |  | Instructions manual in accordance with Machinery Directive 2006/42/EC.
6.3 |  |  |  | Safety instructions |  | Included in item 6.2 | revA
6.4 |  |  |  | Maintenance manual(s) with lubrication instructions |  | Included in item 6.2 | revA
6.5 |  |  |  | Fault tracing instructions |  | Included in item 6.2 | revA
6.6 |  |  |  | Preventive maintenance instructions |  | Included in item 6.2 | revA
7 |  |  |  | MANUALS/INSTRUCTIONS
7.1 |  |  |  | Working environment plan |  | NA | revA
7.2 | SD0130-IRA_01 | 1018739-HAS-0033 |  | Installation risk analysis | No | 2026-04-01 | revA | 2026-02-06 | 2026-02-13
revB
revC
7.3 | SD0130-PDR_01 | 1018739-HAS-0034 |  | Spare & wear part list | No | Prel. in offer | revA | 2026-01-15 | 2026-01-22 |  |  | Prel. in offer
[6 empty] | 8w after order | revB |  |  |  |  | S48 by customer servcice
revC
Formulas:
Cutomer expected return date = IF(ISBLANK([Submittal Date]),"",[Submittal Date]+7)
Note on E129: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Boliden doit checker si info dans Junction box sufficient car on ne fournit pas d’armoire élec

## Liste
Approbation client | Statuts approbation
Yes | Refused
No | Commented, to be updated
Approved with comments
Approved