APPENDIX 4 TIME SCHEDULE

Hasler’s comments in yellow

Dates for fulfilment of operations under the Agreement and any giving of necessary documents are set as follows:

PO = Purchase order.

| Nr | Operations milestones for Contractor | Milestone Date (dd-mm-yyyy) | Hasler’s comments |
| --- | --- | --- | --- |
| 1 | Contract Effective Date | 20-02-2026 |  |
| 2 | Delivery of Drawings for manufacturing- for Purchaser Approval | See (1) |  |
| 3 | Delivery of Technical Documentation (Data Sheets etc.) for externally sourced equipment and components- for Purchaser approval (Appendix 6 item 2) | See (2) |  |
| 4 | Layout & Dimensional information including 3D models. | 20-03-2026 | 8 weeks after PO |
| 5 | Delivery of Initial Project Programme | 20-03-2026 |  |
| 6 | Preliminary Loading, Power Consumption & Utility Requirement Information | 20-03-2026 | 8 weeks after PO |
| 7 | Delivery of Manufacturing documentation for review (Appendix 6 item 4) | 20-03-2026 | 4 weeks after GA/PFD/PID Validation No details drawings provided. |
| 8 | Approval of Project Programme and Manufacturing Documentation by Purchaser | 27-03-2026 | 1 week after documents submission |
| 9 | Certified Loading, Power Consumption & Utility Requirement Information | 30-04-2026 |  |
| 10 | Factory Acceptance Test (F.A.T.) of the Equipment at Contractor’s site | 27-02-2027 | 52 weeks EXW Hasler’s factory. See commercial offer for different delivery time regarding the options. |
| 11 | Signature of Factory Acceptance Certificate | 07-03-2027 |  |
| 12 | Delivery of shipping documentation prior to shipping (Appendix 6 item 11) | 07-03-2027 |  |
| 13 | Equipment ready for transport from Contractor’s workshop | 15-03-2027 | See commercial offer for different delivery time regarding the options. |
| 14 | Delivery of As-Build Documentation (Appendix 6 item 8 and 9) | 15-03-2027 |  |
| 15 | Shipping of the Equipment, Road Transport | 17-03-2027 |  |
| 16 | Delivery date of shipping documentation after shipping (Appendix 6 item 11) | 21-03-2027 |  |
| 17 | Delivery Date of the Equipment to Site | 25-03-2027 |  |
| 18 | Take-Over | 30-05-2027 |  |
| 19 | Performance Test period | Period of 180 days from Take-Over |  |
| 20 | Date of Acceptance | 26/11/2027 (180 days after Take-Over) |  |
| 21 | Signature of Acceptance Certificate | 30/11/2027 |  |

(1): The Drawings for manufacturing must be sent by the Contractor to the Purchaser for approval before beginning to manufacture the equipment. If not, the Purchaser can refuse the equipment.

(2): The Contractor shall send all necessary Documents detailing the externally sourced Equipment (Data sheets etc.) to the Purchaser for approval before ordering any Equipment. The Contractor is not authorised to buy Equipment prior to Purchaser Approval.