APPENDIX 6

DOCUMENTATION

FOR THE SUPPLY OF

FILTER BELT EQUIPMENT

FOR

Quinto Plasterboard Plant,

Spain

CONTRACT REFERENCE:

10190-C50-TSP-GMT-001 Rev A

| Item | Documents | Quantity | Latest Date | Language | Hasler’comments |
| --- | --- | --- | --- | --- | --- |
| 1 | Plant Marking. In addition to the equipment manufacturer's standard nameplate; a name plate shall be permanently attached to each all equipment/skids bearing the following information: Equipment Title / Equipment Item Number Skid Supplier’s name and contact details. Plant reference number Saint-Gobain Project number (10190) | One per skid/tank. Physical tag | With Equipment Delivery | English (1 Copy), Spanish (1 Copy) | - One plate for the filter, one for the motor unit, one for the vacuum pump, one for the separator tank and one per CE equipment purchased from a supplier. - From January 2026, depending on developments in the Machinery Directive, paper versions will no longer be mandatory; only digital versions will be required. If paper versions are required, a substantial budget must be allocated given the volume and time involved. - Documents only in English |
| 2 | Project Programme (Item 4 on Appendix 4) | One per month of project | 30 days from PO raised | English |  |
| 3 | All valves and in-line equipment shall be provided with suitable equipment number tags attached to the equipment Tag number to be agreed between parties after equipment design. | Physical tag | With Equipment Delivery | _ | Sant Gobain provides TAG numbers such as RS0540 (Gelsa’s Filter) , which will be used in PID, PFD and other documents. |
| 4 | Preliminary Loading, Power Consumption and Utility Requirement Information. | Electronic copy | 30 days from PO raised | English | 6 weeks after PID/PFD validation |
| 5 | Certified Loading Information. | Electronic Copy | 60 days from PO raised | English |  |
| 6 | Final Power Consumption and Utility Requirement Information. | Electronic Copy | 60 days from PO raised | English |  |
| 7 | Layout and Dimensional information. To be provided as Inventor-compatible 3D models, in addition to 2D layout drawings. | Electronic copy | 30 days from PO raised | English |  |
| 6 | Engineering Line Diagram (ELD), Equipment Lists and IO lists. | Electronic copy | 30 days from PO raised | English | PFD/PID supplied after 8 weeks from Purchase Order (PO) |
| 7 | Manufacturing Drawings for Approval Bought-out parts / equipment data sheet and necessary documentation for Approval | Electronic copy | 60 days from PO raised | English/ Spanish | Manufacturing Drawings not provided, only General Assembly (GA)like Gelsa filter. GA : 8 weeks after PO |
| 8 | Spare Parts List- Including highlighted equipment as per Appendix 1 Specification. | Electronic copy | 60 days from PO raised | English/ Spanish | 6-8 weeks after GA and PFD/PID validation |
| 9 | Installation, Commissioning & Operation Supporting documentation: - Lubrication schedules where applicable - Equipment commissioning check sheets - Finalised motor, gearbox and instrument lists - Operation, Installation and Maintenance manuals for each machine - Equipment certification, whichever is relevant to the country of installation | Electronic copy 1 paper copy | At Factory Acceptance Test | English/ Spanish | IOM, filter notice in English and Spanish. Supplier notice : English only |
| 10 | ‘As-Built’ documents and drawings: - Finalised ‘As Built’ drawings and 3D Models - Finalised Equipment Summary List (with confirmed item references, sizes and materials of construction, as chosen by the Supplier and approved by the Purchaser) - List of Equipment, Fixings and Consumables being delivered to site - Description of any special/specific installation or assembly methods required in the erection / installation - Tests, material and welder’s certificates - Vessel and pipe work materials certification (tightness test, pressure test… - see Appendix 1) | Electronic copy 1 paper copy | With Equipment Delivery | English/ Spanish | Electronioc copy : okay Paper copy : deviated |
| 11 | Final Tests and Inspection Reports for all Equipment | Electronic copy 2 paper copies | 10 days before takeover | English/ Spanish | Paper copy : deviated |
| 12 | CE Marking Documentation (including Declaration) | Electronic Copy and Paper Copy | 10 days before takeover | English/ Spanish | Paper copy : deviated |
| 13 | Shipping Documents as required for Importation | Electronic Copy | 7 days before shipping | English/ Spanish |  |
| 14 | Delivery Documentation Accompanying the Transportation of the Equipment | Electronic Copy | 7 days before shipping | English/ Spanish |  |

- The Supplier must send all documents and documentation requested by the Purchaser as specified below and following the Appendix 4 Time Schedule.

NOTES:

- All 2D drawings should be fully compatible and editable by the Purchaser and/or AutoCAD (version to be confirmed before Order)

- All documentation should be supplied in English (mandatory). All documents should be fully compatible and editable by the Purchaser.

- Documents format : PDF, DWG, Excel, Word