## 1
欧洲化学哈萨克斯坦化工综合体项目
DOC.NO: | [13 empty] | Rev.D01
No. | Issue Date | Sec & Page | Content | Initiator | Vendor Reply(1) |  |  |  | Vendor's Proposal(2) |  | Ans.Date | TCC Comments on Vendor's Proposal | Vendor's Reply to TCC Comments | Remarks / Status
[5 empty] | A | B | C | D | Sec & Page | Content
1 |  |  | Please refer to the scope of delivery in the "Material Requisition for Vacuum Belt Filter”document, and at the same time add the equipment number and quantity. 请参考真空带式过滤机请购文件中的交货范围、同时加上设备编号和数量。 | TCC | [5 empty] | All information can be found in the technical offer. | 2024-10-04 | Please refer to our requisition documents, specify the scope of delivery and mark the equipment number in your PID and technical documentation. 请参考我们请购文件,明确供货范围，并且在你们PID以及技术文件中按照标注设备位号. |  |  | 所有信息均可在技术资料中找到。
2 |  |  | FILTRATE PUMP 1: No need for supplies. "FILTRATE PUMP 2 & 3", Quantity:4 ;Material: CS RL FILTRATE PUMP 1不需要供货；FILTRATE PUMP 2 & 3 数量：4台，材质：CS RL | TCC | [5 empty] | OK | 2024-10-04
3 |  |  | CLOTH & BELT RECIRCULATING PUMP Quantity:2； Material: CS RL CLOTH & BELT RECIRCULATING PUMP 数量：2台，材质：CS RL CLOTH AND BELT WASHING TANK & PUMP Quantity:2； Material: CS RL CLOTH AND BELT WASHING TANK & PUMP 数量：2台，材质：CS RL | TCC | [5 empty] | OK | 2024-10-04
4 |  |  | "SCRUBBER" Material: CS RL；FILTRATE RECEIVER，Material: CS RL SCRUBBER 材质：CS RL；FILTRATE RECEIVER 材质：CS RL； | TCC | [5 empty] | OK | 2024-10-04
5 |  |  | Please provide FLT 36-100, FLT 56-100 calculation sheet. 请提供真空皮带过滤机的计算书 | TCC | [5 empty] | Our sizing is based on our knowledge and references throughout the world. This kind of document cannot be transmitted. In addition, for these offers we used the sizes you gave us for sizing. | 2024-10-04 | Other manufacturers can provide, please provide VBF data sheet. 其他厂家可以提供， |  |  | 我们的尺寸是根据我们的知识和世界各地的参考资料确定的。此类文件无法传送。 此外，在提供这些产品时，我们使用了您提供的尺寸。
6 |  |  | Please provide vacuum belt filter process conditions. 根据真空带式过滤机工艺数据单，补充真空带式过滤机操作参数， | TCC | [5 empty] | All information will be transmitted to you in the P&ID. | 2024-10-04 | OK |  |  | 所有信息都将通过 P&ID 传输给您。
7 |  |  | FLT 36-100：Filter cake guarantee value ≥35t/h under normal working conditions, ≥40.3t/h under maximum working conditions. FLT 55-100：Filter cake guarantee value ≥45.1t/h under normal working conditions and ≥65.5t/h under maximum working conditions. FLT 36-100：正常工况下滤饼保证值≥35t/h，最大工况下≥40.3t/h。 FLT 55-100：正常工况下滤饼保证值≥45.1t/h，最大工况下≥65.5t/h。 | TCC | [5 empty] | Sizing is based on your process specifications: “PRO-7G25-4xxxxx”. FLT 36-100 : 32,8 t/h FLT 55-100 : 41,4 t/h | 2024-10-04 | Please refer to the latest version of the requisition document 请参考最新版的请购文件
8 |  |  | Provide an automatic control system and emergency protection system. 提供自动控制系统和紧急保护系统。 | TCC | [5 empty] | Detailed in the “electrical control cabinet” section of the technical offers | 2024-10-04 | OK |  |  | 详见技术资料中的 “电气控制
9 |  |  | The cloth wash is performed with process water,The water from cloth wash is sent to a settler (CLR 36-420) to separate the solids. 用工艺水冲洗滤布，洗布水被送入沉淀器（CLR 36-420）分离固体。 | TCC | [5 empty] | The water used must correspond to the water quality listed on the last page of the technical offers. | 2024-10-04 | Please refer to the design basis for our water quality requirements 我们水质要求请参考设计基础， |  |  | 使用的水必须符合技术报价表最后一页所列的水质。
10 |  |  | All the parts in contact with fluid (liquid or gas) and surroundings the filter: rubberlined carbon steel Filter cloth: polypropylen monofilament. Vacuum belt filterand supply equipment need to consider the corrosion and wear resistance of the material. 与流体（液体或气体）接触的所有部件以及过滤器周围：CS RL 滤布：聚丙烯。 真空带式过滤机和供应设备需要考虑材料的耐腐蚀性和耐磨性。 | TCC | [5 empty] | All materials used are described in our technical offers and in accordance with other references we have in these processes. | 2024-10-04 | We require CS RL for all parts in contact with the fluid and around the filter.Please provide a deviation table for those parts that do not meet the requirements. 我们要求是与流体接触的所有部件及过滤器周围都使用CS RL，不满足要求的部分请提供偏差表 |  |  | 所有使用的材料都在我们的技术资料中有所说明，并符合我们在这些工艺中的其他参考资料。
11 |  |  | Supplier to provide the cycle time and filter cloth air coefficient (kg/h/m²) 供应商提供循环时间及滤布空气系数（kg/h/m²）。 | TCC | [5 empty] | We used the sizes you gave us for sizing. Filterability and cycle time are linked to this. | 2024-10-04 |  |  |  | 我们使用您提供的尺寸来确定大小。过滤性和循环时间都与此有关。
12 |  |  | Equipment will be designed for an on-stream factor of 24h/day, 365 days/year. 设备按每年 365 天、每天 24 小时的运行系数设计。 | TCC | [5 empty] | OK | 2024-10-04
13 |  |  | Provides CLR 56-420, CLR 36-420 process data sheets 提供CLR 56-420、CLR 36-420工艺数据单 | TCC | [5 empty] | To be clarified | 2024-10-04 |  |  |  | 有待澄清
|  |  | Please provide proposed layout, equipment weight, utility consumption list. 请提供建议布置图，设备荷载，公用工程消耗清单。 | TCC | [5 empty] | Please refer to our technical offers, GA and P&ID | 2024-10-04 |  |  |  | 请参考我们的技术报价、GA 和 P&ID
TCC
|  |  | We have updated the FLT 56-100 datasheet to the attached PID. The effective filter area of the FLT 56-100 has been changed to a minimum of 95m2,The belt filter is sized for a gypsum filtration of 45.1 t/h. 我们更新了FLT 56-100数据单见附件PID。FLT 56-100有效过滤面积改为最低应为95m2，处理能力改为： 45.1t/h | TCC
|  |  | Provide the following sensors, alarms and automatic interlocks for belt conveyors, including vacuum filter belt conveyors: 1. Conveyor stop and alarm via belt slip sensor; 2. conveyor stop and alarm when critical parameters are reached by speed sensors; 3. conveyor stop and alarm based on the guard removal sensor; 4. onveyor stop and alarm via belt break sensor; 5. Conveyor stop and alarm via belt slip sensor. В. Ensure that the following technical measures are in place for belt conveyors, including vacuum filter belt conveyors: 1. Belt deflection switch (anti-bias switch). Used to detect the deviation of the conveyor belt conveyor belt, and is a safety device to automatically alarm and shut down the conveyor belt when a deviation occurs; 2. Belt deviation correction devices. Sensor rollers detect the deviation of the belt and then return it to the desired path. | TCC
|  |  | Please refer to the design basis for our water quality requirements 我们水质要求请参考设计基础， | TCC
|  |  | FLT 36-100 wash water: 38 m3/h; FLT 56-100 wash water: 33 m3/h. FLT 36-100 洗水量为：38 m3/h; FLT 56-100 洗水量为：33 m3/h; | TCC
|  |  | Please provide Filter Washing proposal in the technical documentation 请在技术文件中提供过滤器清洗方案 | TCC
|  |  | Please provide Filter Washing proposal and inspection timein the technical documentation 请在技术文件中提供过滤器清洗方案和检修时间。 | TCC
|  |  | Mechanical requirements please refer to attachment “MEC-7G02-84-33-005-REQ_0_A_EN_IFR Material Requisition for Belt Conveyor, chaper 3.2". Contain: 1 All conveyors shall be DT(II) A type. 2 All splices shall be vulcanized unless otherwise specified. 3 Normally, the belt conveyor should be driven by single motor, and the motor shall be located at the head pulley unless noted otherwise. 4 All belt conveyors shall uses troughing idlers with an angle of 35° 5 Normally, convex vertical curve conveyors and concave vertical curve conveyors should use troughing idlers instead of bend pulley at convex and concave position unless noted otherwise. 6 All belt conveyors shall be equipped with training idlers. 7 Screw take-up used on conveyors less than 50m long. Gravity take-ups shall be provided on all conveyors over 50m long and on all conveyors with belt scales regardless of length. Minimum tension of the gravity take-ups shall be used for good conveyor operation. 8 All belt conveyors shall be equipped with belt cleaners. It shall be set at the bottom of the head pulley. 9 At loading points, belt conveyors shall be provided with steel plate skirtboards complete with rubber skirts. Skirtboards shall be set at least 4.5m, and provided with top cover plate unless noted otherwise. 10 To against belt damage caused by lateral movement or misalignment, limit switches shall be provided. Two sets of misalignment switches shall be provided. The first set will alarm and the second set will shut down and alarm. 11 A zero speed protection switch or sensor shall be provided on all conveyors to detect belt slippage or breakage from a slow-down in belt speed. 12 All conveyors shall have a continuous pull cord connected to limit switches spaced not more than 50m apart. Switches shall be two direction pull type with no dead end tie-downs. For conveyors with access on both sides of the conveyor a continuous pull cord to limit switches shall be provided on each side. 13 Protective guards shall be provided around drives, take-ups, tail pulleys, take-up carriages and rotating drive elements. All the guards shall be easy removal and service of guarded equipment. All guards shall be painted safety yellow unless noted otherwise. 14 Refer to Att.1 Equipment data sheet of Belt Conveyor. | TCC
|  |  | Please refer to the attached technical requirements provided by the Licensor 请参考附件专利商提供的技术要求 | TCC
TCC
TCC
TCC
TCC
TCC
TCC
TCC
TCC
TCC
TCC
TCC
TCC
TCC
TCC
TCC
TCC
TCC
44 |  |  |  | TCC
45 |  |  |  | TCC
46 |  |  |  | TCC
47 |  |  |  | TCC
48 |  |  |  | TCC
49 |  |  |  | TCC
1. For "Vendor Reply" row, A --- Comply, B --- Not Comply, C --- Comply with Cost Effects, D --- Comply with Deviation/Exception
2. If B/C/D is selected or N.A. for A/B/C/D please also fill "Vendor's Proposal" row